📄 AGROHOUSE FOUNDATION

PROGRAM 2

Farm Infrastructure & Operations System

Prepared By:
Maggie Baty

Organization:
AgroHouse Foundation

Date:
[Insert Date]

1. PURPOSE

Program 2 establishes the full agricultural and infrastructure system of the AgroHouse Foundation.

It creates:

- crop production systems

- livestock and poultry systems

- food flow from production to distribution

- controlled movement and biosecurity systems

Program 2 builds the operational environment that supports long-term sustainability and integrates with Program 1 and future Program 3 systems.

2. SCOPE

Program 2 includes:

- crop production systems

- livestock and poultry systems

- farm infrastructure and layout

- utilities (water and electrical distribution)

- biosecurity and access control systems

- farm stand and basic food handling support

Program 2 excludes:

- workforce curriculum design

- AgroHouse program implementation

- full residential staffing and supervision structure

3. SYSTEM COMPONENTS

3.1 Crop Production System

Includes:

- raised bed systems

- row crop systems

- perennial crops (berries)

- seasonal crops (melons, pumpkins, etc.)

- sunflower and corn systems

Infrastructure:

- irrigation system

- soil management

- designated production zones

Function:

- primary food production

- farm stand supply

- kitchen support

- educational pathway integration

3.2 Livestock System

Includes:

- cattle grazing areas

- swine systems

- quarantine areas

- manure management

Function:

- controlled livestock production

- educational observation areas

- separation from public zones

3.3 Poultry System

Includes:

- breeder systems

- layer pasture

- feeder systems

- incubation and brood houses

Access Types:

- observation only (breeders, feeders)

- conditional interaction (layers)

- controlled interaction (teaching zones)

3.4 Waterfowl System

Includes:

- constructed pond

- geese and duck systems

- supporting structures

Function:

- integrated farm feature

- fertilization support

- observation and educational use

3.5 Farm Stand System

Includes:

- centralized structure

- produce distribution

- public interaction zone

Function:

- primary revenue point

- public access interface

- separation between public and operations

3.6 Food Handling System

Produce Flow:

Crops → Produce Storage → Kitchen → Farm Stand

Meat Flow:

Livestock → Processing → Meat Storage → Kitchen (controlled use)

Components:

- produce cold storage

- secured meat locker (restricted access)

- basic kitchen operations (phased build)

3.7 Utilities System

Electrical:

- grid-powered

- supports lighting, refrigeration, and operations

- distributed across zones

Water:

- irrigation systems

- animal systems

- sanitation stations

3.8 Biosecurity System

Includes:

- north/south separation

- controlled entry points

- sanitation stations

- livestock barriers

Function:

- prevent contamination

- control human and equipment movement

- enforce clean vs operational zones

3.9 Path & Movement System

Includes:

- designated pedestrian pathways

- UTV routes

- educational path across farm

Rules:

- no unrestricted movement

- all transitions controlled

- barriers enforced between systems

3.10 Access Control System

Includes:

- gate-based entry

- badge-controlled access

- role-based movement permissions

Access Levels:

- public (farm stand only)

- workforce (restricted zones)

- operations (full access)

4. OPERATIONAL WORKFLOW

Farm Production Flow

Planting → Growth → Harvest → Storage → Distribution

Livestock Flow

Intake → Care → Management → Processing → Storage

Public Flow

Parking → Farm Stand → Exit

Internal Movement

North Campus → Biosecurity Barrier → Farm Systems → Return

5. FACILITY REQUIREMENTS

Required (Phase 1–2)

- crop systems

- livestock areas

- poultry systems

- irrigation

- basic fencing and gates

- farm stand

- produce storage

Required (Phase 3)

- kitchen (operational)

- meat locker

- expanded infrastructure

6. COST STRUCTURE

Startup Cost Range (Phase 1–2)

$250,000 – $500,000

Full System Cost

$900,000 – $1.6M

Core Cost Breakdown

Crop Systems
$28K – $63K

Livestock & Poultry Systems
$45K – $110K

Utilities (water & electric)
$16K – $40K

Equipment (tractor, UTV, trailer)
$35K – $60K

Biosecurity, fencing, paths
$25K – $70K

Farm Stand
$12K – $30K

Storage Systems
$20K – $60K

7. FUNDING STRUCTURE

Primary:

- federal agricultural grants

- infrastructure grants

Secondary:

- donations

- partnerships

Support:

- revenue from farm stand and food programs

8. INCOME SOURCES

- farm stand sales

- produce sales

- eggs and livestock products (phased)

- food program revenue

- partnerships and contracts

9. PERFORMANCE METRICS

Operational:

- crop yield

- livestock health

- production consistency

Financial:

- revenue per acre

- farm stand performance

- cost per unit production

Strategic:

- system expansion readiness

- integration with outreach

- funding growth

10. ROLE IN FULL SYSTEM

Program 2 serves as the production and infrastructure engine of the AgroHouse Foundation.

It supports:

- Program 1 (food sourcing and operational growth)

- Program 3 (future workforce environment)

- Program 4 (biosecurity and control system)

11. PHASE STRUCTURE

Phase 1

- basic crop systems

- initial livestock

- minimal infrastructure

Phase 2

- farm stand

- expanded crops and animals

- storage systems

Phase 3

- kitchen

- full food system

- operational scaling

12. LOCK STATEMENT

Program 2 is fully defined as the agricultural and infrastructure system for the AgroHouse Foundation.

It is:

- operationally structured

- scalable

- fundable

- aligned with phased development

No additional system design is required prior to engineering and construction