AGROHOUSE FOUNDATION™

Sustainable Food Systems • Workforce Pathways • Community Stability

Mission • Governance • Programs • Budget • Revenue • Grant Strategy • Compliance • Formation Roadmap

Prepared for prospective board members, program partners, and funders

Maggie Baty, Founder & Executive Director

813-364-3921 • LadyOTheMoon@gmail.com

July 2026

© 2026 AgroHouse Foundation™ — Maggie Baty. All Rights Reserved.

Table of Contents

Executive Summary	1

Founders Story	1

Mission & Vision	1

Community Partnership Model & Data Disclosure	1

Program Overview — Four Integrated Components	1

Program 1 — Outreach Stabilization & Operations Activation	1

Program 2 — Farm Infrastructure & Operations System	1

Program 2 — Licensing & Regulatory Compliance	1

Program 2 — Livestock & Avian Veterinary Care	1

Program 3 — Workforce, Education & Training System	1

Program 4 — AgroHouse™ Residential System (Deferred)	1

Formation & Compliance Roadmap	1

Budget Summary by Program	1

Revenue Projections by Program	1

Grants & Funding Strategy by Program	1

Compliance Gap-Check Summary	1

Governance — Bylaws	1

Conflict of Interest Policy	1

Copyright & Ownership Notice	1

# Executive Summary

AgroHouse Foundation™ is a phased nonprofit initiative designed to improve community stability through four interconnected systems:

- Outreach Stabilization

- Agricultural Production

- Workforce and Education Development

- Future Vocational Housing

The Foundation's immediate focus is launching Program 1 and Phase 1 Farm Infrastructure (Program 2). Programs 3 and 4 represent future expansion phases that will be developed only after operational and financial stability is achieved. The long-term goal is to create a sustainable ecosystem where food production, education, workforce development, and community support reinforce one another.

Current Phase & Funding Priorities

Current Development Phase

AgroHouse Foundation™ is currently focused on launching Program 1 (Outreach Stabilization & Operations Activation) and Phase 1–2 of Program 2 (Farm Infrastructure & Operations System). These founder-led programs establish the operational foundation necessary for future workforce, education, and residential initiatives.

Current Funding Goal

Founder-Led Launch Phase:

$320,000–$650,000

Current Priorities

- Complete incorporation and obtain EIN

- Secure 501(c)(3) status

- Recruit and seat the initial Board of Directors

- Establish community partnerships and MOUs

- Launch Program 1 outreach operations

- Develop Phase 1 farm infrastructure

- Pursue grant and foundation funding opportunities

Future Expansion

Programs 3 (Workforce Development & Education) and 4 (AgroHouse™ Residential System) will be developed only after operational and financial stability has been demonstrated through Programs 1 and 2.

# Founders Story

AgroHouse Foundation™ was not created from a formal business plan or grant proposal. It grew from direct observation, community involvement, and a simple question: Why are we treating symptoms when we could be building systems? While volunteering with local community outreach efforts, I spent time helping serve individuals experiencing food insecurity and instability. As I became more involved, I began asking questions about where food came from, how it was sourced, and whether there was a way to provide healthier, more consistent options. I saw dedicated people working hard to help others, but I also saw the challenges that many grassroots outreach programs face limited resources, inconsistent food sources, and little control over the nutritional quality of what could be offered. At the same time, I was operating a small breeding farm and had already spent several years working with waterfowl and livestock systems. That experience led me to consider whether agriculture could play a larger role in supporting community outreach. What began as an idea to produce food for local outreach efforts quickly evolved into a much larger question: What if agriculture, education, workforce development, and community support could be connected into a single system? As I continued researching existing agricultural, educational, and workforce models, I discovered examples of integrated agricultural living systems that combined food production, sustainability, and practical learning. Those concepts inspired the early vision for AgroHouse™ and helped shape the Foundation's long-term approach to creating self-sustaining opportunities rather than temporary solutions. My own background also contributed significantly to the Foundation's development. Originally from the Kansas City area, I grew up surrounded by agriculture and rural communities. Fields of corn, wheat, barley, and sunflowers were a normal part of everyday life, as were livestock operations, cattle ranches, and the seasonal rhythms that come with farming. Agriculture was never an abstract concept—it was simply part of the landscape and culture around me. Growing up in that environment gave me an appreciation for the role agriculture plays in feeding communities, supporting local economies, and creating opportunities for families to build stable lives. While I do not claim to be an expert crop producer, those experiences taught me that farming is ultimately a practical skill built through knowledge, observation, hard work, and continual learning. That perspective has shaped the Foundation's approach from the beginning: agricultural skills can be learned, shared, and used to create long-term community benefits. Combined with several years of hands-on experience raising and breeding waterfowl, those early influences helped me see agriculture not only as a means of producing food, but also as a platform for education, workforce development, and community engagement.

These experiences ultimately led to the development of the AgroHouse Foundation™ model. A phased system that combines Outreach Stabilization, Agricultural Production, Workforce Development & Education, and future Vocational Housing. Rather than addressing individual challenges in isolation, AgroHouse Foundation™ is designed to create interconnected solutions that strengthen food security, expand educational opportunities, develop workforce skills, and promote long-term community stability.

The Foundation exists because meaningful change requires more than temporary assistance-it requires systems that help people build sustainable futures.

# Mission & Vision

## Mission

AgroHouse Foundation™ exists to develop sustainable food production systems, workforce development pathways, and vocational opportunities that support community stability and long-term independence.

## Vision

- Food is produced locally and sustainably

- Outreach is stable and consistent

- Individuals have opportunities to learn, work, and grow

- Communities are supported through structured, long-term solutions

## Core Principle

AgroHouse Foundation™ is not a single program — it is an integrated system where each component builds upon and strengthens the others over time. Four components are developed in phases but function together as one system: Outreach Stabilization, Agricultural Production, Workforce Development, and the AgroHouse™ Vocational Housing System.

## Core Values

- Stability — building consistent and reliable systems

- Structure — creating clear, repeatable operations

- Sustainability — focusing on long-term solutions

- Opportunity — providing pathways for growth and development

- Respect — supporting individuals without pressure or obligation

# Community Partnership Model & Data Disclosure

AgroHouse Foundation™ is designed to work alongside existing organizations, not in place of them. Community partners provide outreach and connection; AgroHouse Foundation™ provides structure, systems, and long-term support.

## Disclosure on Program Sizing

Program 1 is sized using the current, publicly observable service volume of two community outreaches the founder personally attends and serves: approximately 100 individuals served on weekdays (minimum) and approximately 150 individuals served on Sundays. These figures reflect the founder's direct, first-hand observation of need at these two locations. AgroHouse Foundation™ does not currently hold a formal partnership, memorandum of understanding, or data-sharing agreement with either outreach. Formalizing a written partnership agreement with each outreach is a near-term priority and a stated goal of this package — not a claim of an existing partnership. This disclosure is included so that board members, funders, and reviewing agencies have an accurate picture of the program's current relationships.

# Program Overview — Four Integrated Components

AgroHouse Foundation™ operates through four integrated components, developed in sequence: Outreach Stabilization → Agricultural Production → Workforce Development → Vocational Housing Expansion. Each phase builds on the last; nothing is replaced as the system grows.

# Program 1 — Outreach Stabilization & Operations Activation

Status: Founder-led. Executable immediately — no additional infrastructure or design required to begin.

Establishes consistent food distribution, basic operational workflows, early revenue generation, and community visibility. Operates independently of the farm build-out.

## Service Basis

- Two community outreach sites currently attended by the founder (see Data Disclosure above)

- Weekday attendance: approximately 100 individuals served, minimum

- Sunday attendance: approximately 150 individuals served

- AgroHouse Foundation™ is not yet a formal partner of either outreach — sizing is based on observed need

## Operating Model

- Core assets: delivery vehicle, food handling/material equipment

- Minimum staffing: Program Manager + 1 support worker

- Delivery types: direct delivery, partner deliveries (shelters, churches), event-based distribution

- Startup cost range: $70,000 – $150,000

- Primary funding: federal/state grants; secondary: donations and community partners

# Program 2 — Farm Infrastructure & Operations System

Status: Founder-led. Structurally defined and fundable; builds the agricultural and infrastructure engine of the Foundation.

Establishes crop production, livestock and poultry systems, farm stand, utilities, and biosecurity/access control, integrating with Program 1 and future Program 3 systems.

## Crop Production — Purpose

Crop systems (raised bed, row crop, perennial, and seasonal production with irrigation) exist to feed the community. All crop output is directed to three purposes: feeding homeless and food-insecure individuals served through Program 1, supplying the public farm stand, and feeding residents of the AgroHouse™ units once Program 4 is active. Crops are not a hobby or ornamental feature — they are the food-security engine of the system.

## Livestock — Purpose (Education and Outreach Only)

Livestock systems (including cattle, swine, and other large-animal species) at AgroHouse Foundation™ exist to support agricultural education, community outreach, and hands-on learning opportunities. These animals are used for supervised educational experiences with schools, FFA chapters, 4-H clubs, volunteers, community partners, and visitors participating in Foundation programs. The farms design includes dedicated teaching pens and observation areas that allow safe public interaction, agricultural demonstrations, and experiential learning while maintaining appropriate animal welfare standards and separation from active farm operations. Livestock is not operated as a commercial meat-production enterprise. The primary purpose of these systems is to promote agricultural awareness, community engagement, and educational programming in support of the Foundation’s mission.

## Poultry & Waterfowl — Dual Purpose

Poultry and waterfowl systems serve both the educational mission (teaching pens, breeder/layer observation areas, FFA/4-H exhibition) and a modest, separate revenue stream through the sale of live birds, hatching eggs, and eggs (see Revenue Projections). This revenue is distinct from — and does not replace — the crop-based food security mission.

## Farm Stand

- Centralized structure for produce distribution and public interaction

- Primary public revenue interface for Program 2

- Separation maintained between public access and working farm operations

## Biosecurity & Access Control

- North/south zone separation between public, teaching, and production areas

- Controlled entry points and sanitation stations

- Role-based access control across all zones

- Livestock and poultry barriers to prevent cross-contamination

## Cost Summary

- Crop systems: raised bed, row crop, perennial and seasonal crops, irrigation

- Livestock & poultry systems with quarantine, breeder, layer, and teaching-pen areas

- Phase 1–2 startup cost range: $250,000 – $500,000

- Full system cost (all phases through kitchen operations): $900,000 – $1,600,000

- Primary funding: federal agricultural and infrastructure grants; supported by farm stand and food program revenue

# Program 2 — Licensing & Regulatory Compliance

Beyond the county/state agricultural business basics already contemplated in Program 2, the following species- and activity-specific licenses and permits apply directly to the AgroHouse Foundation™ farm plan. These were identified through review of current Florida Fish and Wildlife Conservation Commission (FWC), Florida Department of Agriculture and Consumer Services (FDACS), and USDA APHIS guidance.

## Waterfowl (Geese & Ducks) — FWC

Because most species of ducks and geese are classified as wildlife under Florida law, their acquisition, possession, and sale are regulated by FWC and, for federally protected species, by the U.S. Fish and Wildlife Service — separately from FDACS poultry rules.

- FWC Permit to Possess Class III Wildlife for Commercial Use (waterfowl sale) — required to sell any geese/ducks; fee approximately $50/year (F.S. 372.16)

- Captive-reared waterfowl must be kept on the property and never released — required for disease control (F.A.C. 68A-4.005)

- Federally protected species (most breeds other than Pekin) must be marked as captive-reared (leg band, pinioning, or tattoo) per 50 CFR 21.13–21.14

- Federal Form 3-186 (Notice of Waterfowl Sale or Transfer) must be provided to every buyer of federally protected waterfowl

- A federal Waterfowl Sale and Disposal Permit (50 CFR 21.25) is required to sell federally protected species (or their offspring) beyond personal use — recommend confirming current requirements with the USFWS Atlanta regional office at 404-679-7049 before the first commercial sale

## Poultry, Waterfowl & Game Birds — NPIP (Federal/State)

The National Poultry Improvement Plan (NPIP) is a voluntary federal-state-industry disease testing and certification program administered in Florida by FDACS's Division of Animal Industry. NPIP participation is not legally mandatory for a small flock, but it is effectively required for interstate/intrastate movement documentation, most fair and exhibition entry requirements (relevant to FFA/4-H programming), and buyer confidence in hatching-egg and live-bird sales.

- Enroll the flock through FDACS Division of Animal Industry (Dr. Daniel Wolf, (352) 745-2544, PoultryPrograms@FDACS.gov) — a state agent visits the farm to test for Pullorum-Typhoid and other covered diseases

- Testing fees vary by flock size and are set by the Official State Agent; budget an estimated $150–$400/year

- NPIP “U.S. Pullorum-Typhoid Clean” status is generally required before pursuing other NPIP disease programs (e.g., Avian Influenza Monitored)

- A biosecurity plan meeting NPIP Standard E is required to remain in good standing and supports indemnity eligibility in a disease outbreak

## Eggs & Farm Stand Sales — FDACS

- FDACS Limited Poultry and Egg Farm Operation Permit — required to sell shell eggs beyond the small-flock exemption threshold; eggs must be sold in flats/bulk with the required “not graded” placard (minimum 7″×7″)

- FDACS Retail Food Establishment Permit — likely required if the farm stand sells packaged or processed goods beyond raw whole produce and exempt eggs; whole, uncut produce sold direct-to-consumer is generally exempt

- Florida Cottage Food Law may cover certain low-risk, home-prepared items (baked goods, jams, dry herbs) sold at the farm stand without a separate permit, subject to product and sales-channel restrictions

## Agritourism & Educational Walkthroughs — Florida Agritourism Promotion Act

Florida Statutes §570.85–570.89 (the Agritourism Promotion Act) directly cover the planned school, FFA, and 4-H walkthroughs and any future public tours. Key protections and obligations:

- The Act grants liability protection to an agritourism operator for injuries resulting from the “inherent risks” of a farm visit (animal behavior, uneven ground, farm equipment, etc.), provided the required statutory warning notice is posted at the point of entry — exact statutory language required

- No separate FDACS license is required to claim this protection — it is a statutory liability shield, not a permit

- Local governments cannot prohibit or restrict bona fide agritourism activity on agriculturally classified land, which supports the teaching-pen and walkthrough model

- Nonresidential farm buildings hosting agritourism activity for up to 300 people are generally exempt from the Florida Fire Prevention Code (subject to annual inspection) — relevant to any future teaching pavilion or event structure

- Recommend general liability insurance in addition to the statutory protection — the Act limits liability for inherent risks but does not eliminate it entirely (e.g., it does not protect against negligence)

## General Business Licensing

- County occupational license / Business Tax Receipt

- Florida Department of Revenue sales tax certificate (for live-animal, hatching-egg, and farm-stand product sales)

- USDA-inspected slaughter facility use would be required only if the Foundation ever processes meat for sale — not applicable under the current education-only livestock model

# Program 2 — Livestock & Avian Veterinary Care

This was an identified gap in the original Program 2 budget. AgroHouse Foundation™ will retain two veterinary relationships: an avian/exotic veterinarian for poultry and waterfowl, and a mobile large-animal veterinarian for cattle, swine, and other livestock kept in the teaching pens. Both are retained on file for compliance and used as needed — the founder's own waterfowl expertise handles routine husbandry, but a vet of record is required for health certificates, emergency care, and NPIP/biosecurity compliance.

| Veterinary Line Item | Basis | Est. Annual Cost |
| --- | --- | --- |
| Avian/exotic vet — routine visits | ~4 routine exams/yr @ ~$100–$150/visit (avian exam benchmarks) | $500 – $600 |
| Avian/exotic vet — emergency reserve | Unplanned illness/injury reserve | $1,000 – $1,500 |
| Mobile large-animal vet — routine visits | ~4 farm calls/yr @ ~$150–$250/visit (farm-call fee + basic service) | $600 – $1,000 |
| Mobile large-animal vet — emergency reserve | Unplanned illness/injury reserve | $1,500 – $2,500 |
| Estimated Total — Annual Veterinary Budget |  | $3,600 – $5,600 |

Figures above are planning-stage estimates based on published avian/exotic exam pricing and typical mobile farm-call fees; they are not quotes from a specific provider. Confirm actual rates once an avian veterinarian and a mobile livestock veterinarian are formally retained.

# Program 3 — Workforce, Education & Training System

Status: Founder-designed; partial founder involvement until a program partner is identified to lead full build-out.

Provides structured, task-based, work-based learning built directly on Program 2 infrastructure. Training equals real work — participants (residents, volunteers, teens, staff) are assigned to work zones with role-based access and defined supervision.

## Two Distinct Teen Tracks

The teen model has two separate tracks and they are not interchangeable. (1) Education/Observation Track: general teens, and school, FFA, and 4-H groups, participate in observational and classroom-based learning through the Teen Center and supervised teaching-pen walkthroughs — no access to AgroHouse™ residential units. (2) Workforce Track: teens who have reached legal working age may take paid or volunteer working roles on the farm, subject to FLSA and Florida child labor task restrictions. Teens are not permitted inside the AgroHouse™ residential units under any circumstance except as harvest-time volunteers under direct supervision.

## Compliance Framework

- Fully compliant framework: follows FLSA and Florida labor law, including age-based task restrictions (14–15, 16–17, 18+)

- Worker classification (employee, volunteer, trainee) clearly defined to avoid misclassification

- Badge-based access control and defined supervision at every work zone

- Projected investment: $100,000 – $200,000 (early planning estimate, not yet finalized — covers staffing, curriculum, and access/compliance systems; does not duplicate Program 2 capital costs)

# Program 4 — AgroHouse™ Residential System (Deferred)

Status: Founder-designed as systems architect. Intentionally deferred — the founder will not personally operate this program and is seeking a qualified program partner to lead it once phased in.

Provides structured vocational housing integrated with work and daily operations: 4 AgroHouse™ units (gender-separated — Northwest male / Northeast female), each connected to a 1-acre hoop house system, plus a supervised shared recreation and family-reunification area.

- Estimated cost: $325,000 – $840,000 (units, hoop houses, fencing/paths, recreation area)

- Access control via photo ID badge and role-based permissions; no unrestricted movement

- Surveillance covers common/work areas only — explicitly excludes bedrooms, bathrooms, and private living spaces

## Licensing Note — Resident Population Determines the Governing Framework

This program's residents are intended to be adult vocational program participants, not minors placed by the state. If the operating partner confirms an adult-only resident population, the housing will likely fall under general transitional/workforce housing and business licensing rather than child welfare licensure — though local zoning, occupancy, and possibly community residential home siting rules under Ch. 419, F.S. may still apply and should be confirmed with local planning/zoning before construction. If any resident is, or could be, a minor (including through family reunification), Florida law requires licensure as a child-caring agency under Ch. 409.175, F.S., administered by the DCF Office of Licensing — which includes background screening, staff-to-resident ratios, and (for a traditional group home) a capacity cap of 14 beds. This distinction must be resolved with an attorney and the incoming operating partner before Program 4 construction begins; it is the single largest open compliance question in the full four-program system and is the reason the founder has deferred this program rather than DCF and state involvement generally.

# Formation & Compliance Roadmap

AgroHouse Foundation™ has not yet filed for legal incorporation. The mission, programs, governing documents, and budget in this package are fully developed and ready to move forward; the steps below represent the near-term path to full legal and grant-ready status.

| # | Step | Notes | Status |
| --- | --- | --- | --- |
| 1 | File Articles of Incorporation | Florida Division of Corporations | Not yet filed |
| 2 | Obtain Federal EIN | IRS — available same day once incorporated | Pending |
| 3 | Adopt governing documents | Bylaws and Conflict of Interest Policy — drafted, ready for board adoption | Drafted |
| 4 | Seat initial Board of Directors | Minimum 3 members required; actively recruiting | In progress |
| 5 | Open nonprofit bank account | Requires EIN and incorporation | Pending |
| 6 | File IRS Form 1023 / 1023-EZ | 501(c)(3) federal tax-exempt determination | Not yet filed |
| 7 | Florida charitable solicitation registration | Required before public fundraising under FL Solicitation of Contributions Act | Not yet filed |
| 8 | Begin Program 1 operations | Outreach stabilization — can begin once incorporated | Planned |

Typical 501(c)(3) determination timelines: Form 1023-EZ (for smaller organizations) is often processed in a few weeks to a few months; the standard Form 1023 can take several months to a year. Nearly every grant listed in this package requires the determination letter in hand before an application can be submitted — this timeline directly drives grant readiness.

# Budget Summary by Program

## Founder-Led Phase (Programs 1 & 2)

The immediate ask: launching outreach operations and Phase 1–2 farm infrastructure, which the founder will lead directly.

| Program | Scope | Cost Range |
| --- | --- | --- |
| Program 1 | Outreach Stabilization & Operations | $70,000 – $150,000 |
| Program 2 (Phase 1–2) | Farm Infrastructure & Operations | $250,000 – $500,000 |
| Subtotal | Founder-led launch phase | $320,000 – $650,000 |

## Program 2 — Recurring Operating Add-Ons (Not in Startup Range Above)

The startup cost range above covers capital build-out. The following are recurring annual operating costs layered on top once the farm is active — identified as a gap in the original budget.

| Recurring Item | Est. Annual Cost |
| --- | --- |
| Veterinary care (avian + mobile large-animal, routine + emergency reserve) | $3,600 – $5,600 |
| Licensing & permits (FWC waterfowl, NPIP, FDACS egg/food, county, sales tax) | $300 – $750 |
| Estimated Total — Annual Recurring Compliance & Care Costs | $3,900 – $6,350 |

## Full System — All Four Programs

Programs 3 and 4 figures are early planning estimates and will be refined as program partners are identified.

| Program | Scope | Cost Range |
| --- | --- | --- |
| Program 1 | Outreach Stabilization | $70,000 – $150,000 |
| Program 2 (Phase 1–2) | Farm Infrastructure | $250,000 – $500,000 |
| Program 3 (projected) | Workforce, Education & Training | $100,000 – $200,000 |
| Program 4 | AgroHouse™ Residential System (deferred) | $325,000 – $840,000 |
| Total | Full four-program system | $745,000 – $1,690,000 |

For context, Program 2's full system cost — including a fully operational kitchen and expanded infrastructure beyond Phase 1–2 — is estimated at $900,000 – $1,600,000. This is a longer-term figure, not part of the near-term ask.

# Revenue Projections by Program

Program 1 (Outreach) and Program 3 (Workforce & Education) are cost centers by design — their value is in service delivery and grant/contract eligibility, not direct revenue. Program 4 generates no revenue while deferred. Program 2 (Farm Infrastructure) is the system's primary revenue-generating component, through three channels: live-animal and hatching-egg sales, the farm stand, and — once the campus is built — agritourism/education tours and a snack stand.

## Program 2 — Confirmed AgroHouse Foundation™ Pricing

The pricing below is the Foundation's own established pricing for its current breeding stock, not a market estimate.

| Product | Unit Price | Notes |
| --- | --- | --- |
| Embden geese (grow-out) | $30 / bird | Standard grow-out stock |
| Sebastopol geese | $150 / female | Ornamental breed |
| Oregon Mini geese | $750 / bird | Elite show-quality, Holderread-selected line; breeding program starts from 1–2 eggs from the founder's mother's existing flock — offspring for sale are a Year 2–3 revenue stream, not Year 1 |
| Birmingham Roller pigeons | $150 / bird ($300 / pair) | Sold in pairs only |

## Program 2 — Estimated Pricing (Not Yet Set by AgroHouse Foundation™)

The items below do not have confirmed AgroHouse Foundation™ pricing yet. Figures are regional market comparables provided for grant-budget planning purposes only and should be replaced with actual pricing once set.

| Product | Est. Unit Price | Basis |
| --- | --- | --- |
| Chicken hatching eggs (heritage/rare breed) | ~$30–$45 / dozen (12-egg min. order) | Regional heritage-breed hatching-egg market comparable |
| Ducklings | ~$10–$15 / bird | Regional waterfowl-hatchling market comparable |
| Goslings | ~$20–$35 / bird | Regional waterfowl-hatchling market comparable |
| Guinea keets | ~$6–$10 / bird | Regional poultry-hatchling market comparable |
| Table eggs (chicken, farm stand) | ~$5–$7 / dozen | Current Florida farm-stand comparable |
| Rare/heritage breed chickens (if expanded) | TBD | Contingent on future breed-expansion decision |

## Illustrative Year 1 Flock Revenue Scenario

This scenario uses placeholder quantities, not actual production numbers, since flock sizes have not yet been finalized. It exists only so a funder or board member can see how the confirmed pricing above translates into a dollar range at modest volume. Replace the quantity column with real numbers once the Phase 1 flock plan is set.

| Product | Illustrative Qty / Yr | Illustrative Revenue |
| --- | --- | --- |
| Embden geese | 15 | $450 |
| Sebastopol geese | 6 | $900 |
| Oregon Mini geese | 0 (Yr 1) / 2 (Yr 2–3 est.) | $0 — $1,500 |
| Roller pigeon pairs | 10 | $3,000 |
| Chicken hatching eggs (dozens) | 20 | ~$700 |
| Ducklings | 40 | ~$480 |
| Goslings | 20 | ~$500 |
| Guinea Keets | 30 | ~$240 |
| Table eggs (dozens) | 100 | ~$600 |
| Illustrative Year 1 Total (confirmed + estimated lines) |  | ~$6,870 – $8,370 |

## Farm Stand Produce

Crop-based farm stand produce revenue is not modeled here because acreage, crop mix, and yield have not yet been finalized under the Phase 1 crop plan. Once that plan is set, a per-acre revenue estimate can be built using University of Florida IFAS regional produce-price benchmarks.

## Agritourism / Education Tours

Tour and educational-walkthrough pricing cannot be set until the physical campus is built, per the founder — this is not modeled as near-term revenue. Once tours begin, they are covered by the Florida Agritourism Promotion Act's liability framework (see Licensing & Regulatory Compliance) provided the statutory warning notice is posted. Budget for this line once admission pricing is determined.

## Snack Stand

No pricing has been set for the planned farm snack stand. Listed here as a planned future revenue category, not included in current dollar estimates.

## Income Sources Across the System — Summary

- Outreach program funding and food distribution contracts (Program 1)

- Farm stand and produce sales (Program 2)

- Live-animal, hatching-egg, and table-egg sales (Program 2)

- Agritourism/education tour admission — future, once priced (Program 2)

- Snack stand — future, once priced (Program 2)

- Federal, state, and private grant funding (all programs)

- Donations and community/corporate partnerships (all programs)

# Grants & Funding Strategy by Program

Almost every grant below requires the IRS 501(c)(3) determination letter, an EIN, a seated board, and adopted bylaws before an application can be submitted — see the Formation & Compliance Roadmap. This list is organized by program so applications can be targeted rather than general. Deadlines and award amounts shift year to year; confirm current figures on the listed agency site before applying. USDA Rural Development programs are restricted to eligible rural areas (generally population under 20,000–50,000 depending on the program) — confirm the final farm site's eligibility on the USDA Rural Development eligibility map before applying, since parts of the greater Tampa Bay area may not qualify.

## Program 1 — Outreach Stabilization & Operations Activation

| Grant / Program | Source | Typical Award | Fit |
| --- | --- | --- | --- |
| Community Food Projects Competitive Grant (CFPCGP) | USDA NIFA | Planning: $25K–$50K; Full: $125K–$400K (1:1 match required) | Direct fit — food distribution, food insecurity reduction, self-sufficiency |
| Micro-Grants for Food Security Program (MGFSP) | USDA AMS, via FDACS subaward | Small-scale; varies by state allocation | Fits small-scale food-security distribution model |
| Emergency Food and Shelter Program (EFSP) | FEMA, administered locally | Local board-set awards | Direct fit for food distribution operations |
| Feeding Florida network / regional food bank partnerships | Feeding Florida affiliate | In-kind product + pass-through funding | Partnership and product-sourcing channel, not a cash grant |
| Local community/corporate grants (Publix Charities, Walmart Community Grants, local United Way, community foundations serving Pasco/Hillsborough) | Private/corporate | $1K–$25K typical | Accessible before 501(c)(3) determination in some cases (fiscal sponsorship) — good bridge funding |

## Program 2 — Farm Infrastructure & Operations System

| Grant / Program | Source | Typical Award | Fit |
| --- | --- | --- | --- |
| Patrick Leahy Farm to School Grant | USDA Food & Nutrition Service | $100K–$500K (FY26 pool: $18M) | Strong fit — agricultural education, school partnerships, local food sourcing; must partner with a school/CNP site |
| Value-Added Producer Grant (VAPG) | USDA Rural Development | Planning up to $75K / Working capital up to $250K | Fits farm stand product development and marketing |
| Community Facilities Direct Loan & Grant Program | USDA Rural Development | Varies by project, rural-area restricted | Fits farm infrastructure if site qualifies as a rural area — confirm eligibility |
| Environmental Quality Incentives Program (EQIP) | USDA NRCS | Cost-share, project-based | Fits fencing, irrigation, waste management, conservation infrastructure |
| Specialty Crop Block Grant Program | USDA AMS, via FDACS | Varies; state-administered | Fits crop production enhancement, farm stand |
| Rural Community Development Initiative (RCDI) | USDA Rural Development | Varies; rural-area restricted | Fits community/economic development framing of the farm |
| Corporate/foundation agricultural grants (Farm Credit of Florida, John Deere Foundation, Publix) | Private/corporate | Varies | Fits equipment and infrastructure needs |

## Program 3 — Workforce, Education & Training System

| Grant / Program | Source | Typical Award | Fit |
| --- | --- | --- | --- |
| WIOA Youth/Adult workforce funding | U.S. DOL, via CareerSource Florida / CareerSource Pasco Hernando | Varies; contract-based | Strong fit — task-based, work-based learning aligns with WIOA work experience models |
| Beginning Farmer and Rancher Development Program (BFRDP) | USDA NIFA | Varies; competitive | Fits agricultural training curriculum development |
| Florida Job Growth Grant Fund | FL Dept. of Commerce (DEO) | Varies; infrastructure/workforce focus | Potential fit for workforce infrastructure once a public-sector or education partner co-applies |
| National FFA Foundation / Florida FFA Foundation grants | FFA Foundation | Varies; program-specific | Direct fit — supports FFA chapter partnerships and ag-education programming |
| Florida 4-H Foundation grants | UF/IFAS Florida 4-H Foundation | Varies; program-specific | Direct fit — supports 4-H programming and teaching-pen educational use |
| Career and Technical Education (CTE) grants | Florida Dept. of Education | Varies; school-partnership based | Fits workforce/vocational curriculum once a school-district partner is identified |

## Program 4 — AgroHouse™ Residential System (For Future Operating Partner)

Program 4 is deferred by the founder. The grants below are listed so the eventual operating partner is not starting from zero — they are not part of the founder's near-term application plan.

| Grant / Program | Source | Typical Award | Fit |
| --- | --- | --- | --- |
| Farm Labor Housing Direct Loans & Grants (Section 514/516) | USDA Rural Development | Loan + grant combination; project-based | Strong fit — purpose-built for on-farm worker/vocational housing |
| Continuum of Care (CoC) Program | HUD, via local Continuum of Care lead agency | Varies; competitive, local allocation | Fits if residents include individuals transitioning from homelessness |
| State Apartment Incentive Loan (SAIL) / workforce housing programs | Florida Housing Finance Corporation | Varies; competitive | Fits vocational/workforce housing framing |
| Residential child-caring agency funding (only if minors are housed) | DCF, contingent on Ch. 409.175 licensure | Contract-based | Applies only if the operating partner confirms minor residents — see Licensing Note |
| Private/foundation transitional & vocational housing grants | Private/corporate | Varies | Fits general capital and program support |

# Compliance Gap-Check Summary

A quick punch-list of open items identified in this review — none of these block the Saturday conversation, but each should be resolved before the corresponding program moves forward.

- USDA Rural Development program eligibility (Community Facilities, RCDI, Farm Labor Housing) depends on the final farm site qualifying as a rural area — confirm on the USDA eligibility map once the site is finalized

- Program 4 licensing pathway depends entirely on whether any resident is or could be a minor — resolve with an attorney and the incoming operating partner before construction; this is the single largest open question in the plan

- USFWS federal Waterfowl Sale and Disposal Permit requirements and current fees should be confirmed directly with the USFWS Atlanta regional office before the first commercial waterfowl sale

- NPIP enrollment cost is flock-size and testing-frequency dependent — get an exact quote from the FDACS Official State Agent before finalizing the Program 2 operating budget

- FDACS Retail Food Establishment Permit fee schedule should be confirmed directly with FDACS Division of Food Safety, since fees are updated periodically

- General liability and agritourism-specific insurance should be secured before any public tour or school/FFA/4-H walkthrough begins, in addition to the statutory Agritourism Promotion Act protection

- A written partnership agreement (MOU) with each of the two current outreach organizations would materially strengthen every Program 1 grant application — currently no formal agreement exists

- Formal flock/crop production plan (species counts, acreage, planting schedule) is needed to convert the illustrative revenue figures in this package into an actual operating budget line

# Governance — Bylaws

## Article I — Name and Purpose

The name of this organization shall be AgroHouse Foundation™. AgroHouse Foundation™ is organized exclusively for charitable, educational, and nonprofit purposes under Section 501(c)(3) of the Internal Revenue Code.

The organization exists to:

- Provide food assistance through sustainable agricultural systems

- Develop structured workforce training programs

- Offer youth education in agriculture and mechanical skills

- Build long-term community stability systems

- Develop transitional housing through the AgroHouse™ Model

- Support individuals and families experiencing food insecurity

## Article II — Board of Directors

Section 1. Authority

The Board of Directors shall govern the affairs of the organization and ensure alignment with its mission, legal compliance, and financial responsibility.

Section 2. Composition

The Board shall consist of no fewer than three (3) members. Initial board structure may include a Founder/Executive Director, Community/Outreach Representative, Education or Program Representative, Fleet & Mechanical Systems Lead, and additional members as needed.

Section 3. Terms

Board members shall serve two (2) year terms and may be reappointed.

Section 4. Duties

Board members shall provide oversight and governance, approve major decisions and policies, ensure responsible use of funds, support the mission and programs, and maintain compliance with nonprofit laws.

Section 5. Meetings

The Board shall meet at least once annually; additional meetings may be held as needed.

Section 6. Quorum

A majority of the Board shall constitute a quorum.

Section 7. Voting

Each board member shall have one vote. Decisions are made by majority vote unless otherwise specified.

Section 8. Removal

A board member may be removed by majority vote if duties are not fulfilled, actions conflict with the mission, or legal/ethical violations occur.

## Article III — Officers

Section 1. Officers

The organization may include a President (Founder/Executive Director), Secretary, and Treasurer.

Section 2. President / Executive Director

The President shall oversee daily operations, implement board decisions, and lead organizational strategy and development.

## Article IV — Compensation

Section 1. Board Service

Board members shall not receive compensation for board service.

Section 2. Operational Roles

Board members may receive compensation for separate operational roles, provided compensation is reasonable, approved by the Board, and the individual does not vote on their own compensation.

## Article V — Assets and Property

Section 1. Ownership

All organizational assets — including land, vehicles, equipment, and facilities — are owned by AgroHouse Foundation™.

Section 2. Use Restrictions

Assets must be used for mission-related purposes only and shall not be used for personal benefit or private gain.

## Article VI — Conflict of Interest

The organization shall maintain a Conflict of Interest Policy to ensure transparency and ethical decision-making (see the following section).

## Article VII — Dissolution

Upon dissolution, all assets shall be distributed to another 501(c)(3) organization with a similar mission.

## Article VIII — Amendments

These bylaws may be amended by majority vote of the Board of Directors.

# Conflict of Interest Policy

## Article I — Purpose

The purpose of this policy is to protect AgroHouse Foundation™ from conflicts between personal interests and organizational duties.

## Article II — Definition of Conflict

A conflict of interest exists when a person has a financial interest, a personal benefit, or any relationship that could influence decision-making.

## Article III — Covered Persons

This policy applies to board members, officers, and staff in leadership roles.

## Article IV — Duty to Disclose

Each covered person must disclose any actual or potential conflict of interest.

## Article V — Procedures

1. Disclosure

The individual must disclose the conflict to the Board.

2. Recusal

The individual must not participate in discussion when necessary and must not vote on the matter.

3. Determination

The Board shall determine whether a conflict exists and whether the decision is fair and reasonable.

## Article VI — Compensation Conflicts

If a board member is compensated, the compensation must be disclosed, the individual cannot vote on it, and the Board must determine that it is reasonable.

## Article VII — Records

Meeting records must include disclosure of conflicts, actions taken, and final decisions.

## Article VIII — Annual Statement

Each board member shall annually confirm understanding of this policy, agreement to comply, and commitment to disclose conflicts.

## Article IX — Violations

If a conflict is not disclosed, the Board may investigate and appropriate corrective action may occur.

# Copyright & Ownership Notice

© 2026 AgroHouse Foundation™ — Maggie Baty. All Rights Reserved. This document, and the AgroHouse Foundation™ mission, program design, systems, and materials described within it, are the original work product of the founder. No part of this document may be reproduced, distributed, copied, or used to develop a similar program without express written permission from AgroHouse Foundation™.

This package, the AgroHouse Foundation™ name, the AgroHouse™ vocational housing model, and all associated program designs, systems, budgets, and materials represent original work developed by the founder over an extended period. Reproduction, distribution, or derivative use without written permission from AgroHouse Foundation™ is prohibited.